## Exec Summary
mms
Planned Start Date: 22/04/2023 Actual Start Date : 22/04/2023
Planned End Date : 27/04/2023 Actual End Date : 27/04/2023
Liferay - Test Report - Executive Dashboard
Testing Environment : TEST
Feature of Scope:
  Feature Login
  Feature Logout
  Feature Checkout
  ...

## Sheet2 (hidden)
Issue key | Status | Component/s | Priority
COBA-66676 | Done by Product | CHS functionalities | Critical

## Dev progress (hidden)
FS2 development
Test progress | 90%
S1 & S2 issues | 33 | Resolved so far | 26
|  | Av. fix rate | 4.5
Test projection | 100%
Projected S1 & S2 | 36.6667 | Left to do | 10.6667
|  | days | 2.3704
Total S1+S2 |  |  |  | 2017-04-23 | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-04-29 | 2017-04-30 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05
Projected burn down |  |  |  | 2017-04-23: 11; 2017-04-24: 9; 2017-04-25: 9; 2017-04-26: 4.5; 2017-04-27: 0

## S+ design progress (hidden)
Total Number of issues reviewed | 152
Number in don't count /duplicate | 30
Number of issues triaged to standard defect fixing | 54
Fixed in production | 21
In FS1/FS3 development | 33
Number of issues in architecture workstream | 68
Architectural Interest Breakdown
Fixed in production | 21
CTRL Raised | 5
Closed | 6
Root Cause Known | 1
Under Investigation | 35
Under Investigation Breakdown
OSU Baseline | 8
Other | 19
Standard defect process | 6
CTRL raised | 1
Closed | 1

## FS5_NI_BL_Daywise ExecutionPlan (hidden)
NI PMS - Overall - 7.10 - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2017-05-26 | 33 | 30 |  | 2017-05-26 | 33 | 30
| 2017-05-27 | 0 | 0 |  | 2017-05-27 | 33 | 30
| 2017-05-28 | 0 | 0 |  | 2017-05-28 | 33 | 30
| 2017-05-29 | 121 | 121 |  | 2017-05-29 | 154 | 151
| 2017-05-30 | 151 | 164 |  | 2017-05-30 | 305 | 315
| 2017-05-31 | 147 | 161 |  | 2017-05-31 | 452 | 476
| 2017-06-01 | 147 | 147 |  | 2017-06-01 | 599 | 623
| 2017-06-02 | 105 | 81 |  | 2017-06-02 | 704 | 704
| 2017-06-03 | 0 | 0 |  | 2017-06-03 | 704 | 704
| 2017-06-04 | 0 | 0 |  | 2017-06-04 | 704 | 704
| 2017-06-05 | 0 | 0 |  | 2017-06-05 | 704 | 704
| 2017-06-06 | 0 | 0 |  | 2017-06-06 | 704 | 704
| 2017-06-07 | 0 | 0 |  | 2017-06-07 | 704 | 704
| 2017-06-08 | 0 | 0 |  | 2017-06-08 | 704 | 704
| 2017-06-09 | 0 | 0 |  | 2017-06-09 | 704 | 704
| 2017-06-10 | 0 | 0 |  | 2017-06-10 | 704 | 704
| 2017-06-11 | 0 | 0 |  | 2017-06-11 | 704 | 704
| 2017-06-12 | 0 | 0 |  | 2017-06-12 | 704 | 704
| 2017-06-13 | 0 | 0 |  | 2017-06-13 | 704 | 704
| 2017-06-14 | 0 | 0 |  | 2017-06-14 | 704 | 704
| 2017-06-15 | 0 | 0 |  | 2017-06-15 | 704 | 704
| 2017-06-16 | 0 | 0 |  | 2017-06-16 | 704 | 704
| 2017-06-17 | 0 | 0 |  | 2017-06-17 | 704 | 704
| 2017-06-18 | 0 | 0 |  | 2017-06-18 | 704 | 704
| 2017-06-19 | 0 | 0 |  | 2017-06-19 | 704 | 704
| 2017-06-20 | 0 | 0 |  | 2017-06-20 | 704 | 704
| 2017-06-21 | 0 | 0 |  | 2017-06-21 | 704 | 704
| 2017-06-22 | 0 | 0 |  | 2017-06-22 | 704 | 704
| 2017-06-23 | 0 | 0 |  | 2017-06-23 | 704 | 704
| 2017-06-24 | 0 | 0 |  | 2017-06-24 | 704 | 704
| 2017-06-25 | 0 | 0 |  | 2017-06-25 | 704 | 704
| 2017-06-26 | 0 | 0 |  | 2017-06-26 | 704 | 704
| 2017-06-27 | 35 | 36 |  | 2017-06-27 | 739 | 740
| 2017-06-28 | 75 | 75 |  | 2017-06-28 | 814 | 815
| 2017-06-29 | 95 | 95 |  | 2017-06-29 | 909 | 910
| 2017-06-30 | 95 | 95 |  | 2017-06-30 | 1004 | 1005
| 2017-07-01 | 0 | 0 |  | 2017-07-01 | 1004 | 1005
| 2017-07-02 | 0 | 0 |  | 2017-07-02 | 1004 | 1005
| 2017-07-03 | 95 | 115 |  | 2017-07-03 | 1099 | 1120
| 2017-07-04 | 39 | 62 |  | 2017-07-04 | 1138 | 1182
| 2017-07-05 | 60 | 58 | PMS UAT : There is a deviation as training mode for NI is not available to test | 2017-07-05 | 1198 | 1240
| 2017-07-06 | 51 | 26 | There is a deviation of 25 UJ's due to following reasons 1) Training mode for NI is not available to test. 2) Offline UJ's are marked as NA as environment will not be made available for NI to test during FS5 3) Confirmation defects cannot be tested with current 7.10 code as they are fixed in 7.11 code, hence 6 of the UJ's are marked as NA | 2017-07-06 | 1249 | 1266
| 2017-07-07 | 61 | 48 | There is a deviation of 16 UJ's as 3 are blocked due to training mode unavailability and all other UJ's were executed in previous days | 2017-07-07 | 1310 | 1314
| 2017-07-08 | 0 | 0 |  | 2017-07-08 | 1310 | 1314
| 2017-07-09 | 0 | 0 |  | 2017-07-09 | 1310 | 1314
| 2017-07-10 | 46 | 44 | Testing for FS5 is completed with 3 UJ's in blocked state (due to environment unavailability for Training mode). Team is currently focusing on FS4 regression and Repeat management | 2017-07-10 | 1356 | 1358
| 2017-07-11 | 30 | 50 |  | 2017-07-11 | 1386 | 1408
| 2017-07-12 | 30 | 18 |  | 2017-07-12 | 1416 | 1426
| 2017-07-13 | 257 | 209 |  | 2017-07-13 | 1673 | 1635
| 2017-07-13 | 0 | 0 |  | 2017-07-13 | 1673 | 1635
| 2017-07-14 | 0 | 0 |  | 2017-07-14 | 1673
NI PMS - SIT - 7.10 - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2017-05-26 | 23 | 23 |  | 2017-05-26 | 23 | 23
| 2017-05-27 | 0 | 0 |  | 2017-05-27 | 23 | 23
| 2017-05-28 | 0 | 0 |  | 2017-05-28 | 23 | 23
| 2017-05-29 | 104 | 104 |  | 2017-05-29 | 127 | 127
| 2017-05-30 | 118 | 118 |  | 2017-05-30 | 245 | 245
| 2017-05-31 | 118 | 118 |  | 2017-05-31 | 363 | 363
| 2017-06-01 | 119 | 119 |  | 2017-06-01 | 482 | 482
| 2017-06-02 | 77 | 77 |  | 2017-06-02 | 559 | 559
| 2017-06-03 | 0 | 0 |  | 2017-06-03 | 559 | 559
| 2017-06-04 | 0 | 0 |  | 2017-06-04 | 559 | 559
| 2017-06-05 | 0 | 0 |  | 2017-06-05 | 559 | 559
| 2017-06-06 | 0 | 0 |  | 2017-06-06 | 559 | 559
| 2017-06-07 | 0 | 0 |  | 2017-06-07 | 559 | 559
| 2017-06-08 | 0 | 0 |  | 2017-06-08 | 559 | 559
| 2017-06-09 | 0 | 0 |  | 2017-06-09 | 559 | 559
| 2017-06-10 | 0 | 0 |  | 2017-06-10 | 559 | 559
| 2017-06-11 | 0 | 0 |  | 2017-06-11 | 559 | 559
| 2017-06-12 | 0 | 0 |  | 2017-06-12 | 559 | 559
| 2017-06-13 | 0 | 0 |  | 2017-06-13 | 559 | 559
| 2017-06-14 | 0 | 0 |  | 2017-06-14 | 559 | 559
| 2017-06-15 | 0 | 0 |  | 2017-06-15 | 559 | 559
| 2017-06-16 | 0 | 0 |  | 2017-06-16 | 559 | 559
| 2017-06-17 | 0 | 0 |  | 2017-06-17 | 559 | 559
| 2017-06-18 | 0 | 0 |  | 2017-06-18 | 559 | 559
| 2017-06-19 | 0 | 0 |  | 2017-06-19 | 559 | 559
| 2017-06-20 | 0 | 0 |  | 2017-06-20 | 559 | 559
| 2017-06-21 | 0 | 0 |  | 2017-06-21 | 559 | 559
| 2017-06-22 | 0 | 0 |  | 2017-06-22 | 559 | 559
| 2017-06-23 | 0 | 0 |  | 2017-06-23 | 559 | 559
| 2017-06-24 | 0 | 0 |  | 2017-06-24 | 559 | 559
| 2017-06-25 | 0 | 0 |  | 2017-06-25 | 559 | 559
| 2017-06-26 | 0 | 0 |  | 2017-06-26 | 559 | 559
| 2017-06-27 | 20 | 20 |  | 2017-06-27 | 579 | 579
| 2017-06-28 | 60 | 60 |  | 2017-06-28 | 639 | 639
| 2017-06-29 | 80 | 80 |  | 2017-06-29 | 719 | 719
| 2017-06-30 | 80 | 80 |  | 2017-06-30 | 799 | 799
| 2017-07-01 | 0 | 0 |  | 2017-07-01 | 799 | 799
| 2017-07-02 | 0 | 0 |  | 2017-07-02 | 799 | 799
| 2017-07-03 | 80 | 80 |  | 2017-07-03 | 879 | 879
| 2017-07-04 | 20 | 21 |  | 2017-07-04 | 899 | 900
| 2017-07-05 | 20 | 20 |  | 2017-07-05 | 919 | 920
| 2017-07-06 | 15 | 15 |  | 2017-07-06 | 934 | 935
| 2017-07-07 | 35 | 35 |  | 2017-07-07 | 969 | 970
| 2017-07-08 | 0 | 0 |  | 2017-07-08 | 969 | 970
| 2017-07-09 | 0 | 0 |  | 2017-07-09 | 969 | 970
| 2017-07-10 | 35 | 40 |  | 2017-07-10 | 1004 | 1010
| 2017-07-11 | 30 | 50 |  | 2017-07-11 | 1034 | 1060
| 2017-07-12 | 30 | 18 |  | 2017-07-12 | 1064 | 1078
| 2017-07-13 | 257 | 209 |  | 2017-07-13 | 1321 | 1287
| 2017-07-14 | 0 | 5 |  | 2017-07-14 | 1321 | 1292
NI PMS - UAT - 7.10- Day Wise Execution Plan
Cumulative
| Date | Planned User Journeys | Actual User Journeys | Reason for Deviation | Date | Planned User Journeys | Actual User Journeys
| 2017-05-26 | 10 | 7 | There is a deviation in the planned and actual User Journey's as offshore NI store was ready with shakedown completed and onshore NI stores have shakedown yet to be completed | 2017-05-26 | 10 | 7
| 2017-05-27 | 0 | 0 |  | 2017-05-27 | 10 | 7
| 2017-05-28 | 0 | 0 |  | 2017-05-28 | 10 | 7
| 2017-05-29 | 17 | 17 |  | 2017-05-29 | 27 | 24
| 2017-05-30 | 33 | 46 |  | 2017-05-30 | 60 | 70
| 2017-05-31 | 29 | 43 |  | 2017-05-31 | 89 | 113
| 2017-06-01 | 28 | 28 |  | 2017-06-01 | 117 | 141
| 2017-06-02 | 28 | 4 | There is a deviation as UJ's planned for today have been executed in previous days | 2017-06-02 | 145 | 145
| 2017-06-27 | 15 | 16 |  | 2017-06-27 | 160 | 161
| 2017-06-28 | 15 | 15 |  | 2017-06-28 | 175 | 176
| 2017-06-29 | 15 | 15 |  | 2017-06-29 | 190 | 191
| 2017-06-30 | 15 | 15 |  | 2017-06-30 | 205 | 206
| 2017-07-01 | 0 | 0 |  | 2017-07-01 | 205 | 206
| 2017-07-02 | 0 | 0 |  | 2017-07-02 | 205 | 206
| 2017-07-03 | 10 | 30 |  | 2017-07-03 | 215 | 236
| 2017-07-04 | 10 | 30 |  | 2017-07-04 | 225 | 266
| 2017-07-05 | 31 | 28 | There is a deviation of 3 UJ's as training mode for NI is not available to test | 2017-07-05 | 256 | 294
| 2017-07-06 | 31 | 6 | There is a deviation of 25 UJ's due to following reasons 1) Training mode for NI is not available to test. 2) Offline UJ's are marked as NA as environment will not be made available for NI to test during FS5 3) Confirmation defects cannot be tested with current 7.10 code as they are fixed in 7.11 code, hence 6 of the UJ's are marked as NA | 2017-07-06 | 287 | 300
| 2017-07-07 | 14 | 1 | There is a deviation of 16 UJ's as 3 are blocked due to training mode unavailability and all other UJ's were executed in previous days | 2017-07-07 | 301 | 301
| 2017-07-08 | 0 |  |  | 2017-07-08 | 301 | 301
| 2017-07-09 | 0 |  |  | 2017-07-09 | 301 | 301
| 2017-07-10 | 0 | 0 | Testing for FS5 is completed. Training mode and Offline UJ's are marked as NA as they are moved to FS5 regression scope. Team is currently focusing on FS4 regression and Repeat management | 2017-07-10 | 301 | 301
Wales Stock+- SIT & UAT - 7.10 - Day Wise Execution Plan
Cumulative
| Date | Planned User Journeys | Actual User Journeys | Reason for Deviation | Date | Planned User Journeys | Actual User Journeys
| 2017-07-03 | 5 | 5 |  | 2017-07-03 | 5 | 5
| 2017-07-04 | 9 | 11 |  | 2017-07-04 | 14 | 16
| 2017-07-05 | 9 | 10 |  | 2017-07-05 | 23 | 26
| 2017-07-06 | 5 | 5 |  | 2017-07-06 | 28 | 31
| 2017-07-07 | 12 | 12 |  | 2017-07-07 | 40 | 43
| 2017-07-08 | 0 |  |  | 2017-07-08 | 40 | 43
| 2017-07-09 | 0 |  |  | 2017-07-09 | 40 | 43
| 2017-07-10 | 11 | 4 | NI Baseline testing completed, 4 tests are blocked | 2017-07-10 | 51 | 47
| 2017-07-11 | 0 |  |  | 2017-07-11 | 51
| 2017-07-12 | 0 |  |  | 2017-07-12 | 51
Formulas:
Date = [Date]

## FS5_NI_BL_Progress by Function (hidden)
Test Execution Status From ALM - Columbus NI 7.10 - Overall | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
Basic Dispensing | 340 | 169 | 340 | 0 | 306 | 34 | 0 | 0 | 0 | 66.8% | 90%
Label Printing | 76 | 0 | 76 | 0 | 66 | 10 | 0 | 0 | 0 | 100% | 86.84%
Patient Management | 28 | 2 | 28 | 0 | 22 | 6 | 0 | 0 | 0 | 93.33% | 78.57%
Prescriber and Practice Management | 25 | 7 | 25 | 0 | 20 | 5 | 0 | 0 | 0 | 78.12% | 80%
Endorsement | 125 | 17 | 125 | 0 | 114 | 11 | 0 | 0 | 0 | 88.03% | 91.2%
2DRx | 297 | 38 | 292 | 0 | 280 | 12 | 2 | 0 | 3 | 87.16% | 95.89%
MUR | 32 | 2 | 22 | 0 | 14 | 8 | 0 | 10 | 0 | 64.71% | 63.64%
Nexphase Migration | 243 | 0 | 242 | 0 | 237 | 5 | 1 | 0 | 0 | 99.59% | 97.93%
Automation - Installments | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 50% | 100%
Automation -Private prescription report | 16 | 16 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 50% | 100%
Automation - Basic dispensing | 14 | 13 | 14 | 0 | 7 | 7 | 0 | 0 | 0 | 51.85% | 50%
DDS | 4 | 0 | 3 | 0 | 1 | 2 | 1 | 0 | 0 | 75% | 33.33%
Emergency Supply | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 100% | 100%
Instalments | 14 | 6 | 11 | 0 | 13 | 1 | 0 | 0 | 0 | 55% | 118.2%
Simple Instalments | 7 | 0 | 7 | 0 | 6 | 1 | 0 | 0 | 0 | 100% | 85.71%
Offline | 18 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0% | 0%
Owings | 15 | 0 | 15 | 0 | 13 | 2 | 0 | 0 | 0 | 100% | 86.67%
Private Prescription Book | 21 | 16 | 21 | 0 | 19 | 2 | 0 | 0 | 0 | 56.76% | 90.48%
Private Prescriptions | 10 | 0 | 10 | 0 | 9 | 1 | 0 | 0 | 0 | 100% | 90%
Quad Stamp | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 100% | 100%
Reports | 10 | 0 | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 100% | 80%
Scan Article | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 100% | 100%
Shortcut Keys | 5 | 0 | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 100% | 80%
Training Mode | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0% | 0%
Uncatalogued Products | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Vet Dispensing | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Visually Impaired | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100%
Automation - Endorsement | 17 | 17 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 50% | 100%
Automation - 2DRx | 5 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 50% | 100%
Automation - MUR | 2 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 50% | 100%
Automation - Regression | 16 | 16 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 50% | 100%
Defects associated to UJ's | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0% | 0%
Total - FS1 | 1432 | 332 | 1386 | 0 | 1273 | 116 | 26 | 14 | 3 | 78.57% | 91.85%
Defect Validation Testing- Columbus Wales 7.8 -Overall | [9 empty] | As part of the process of running the baseline tests all existing defects will be retested to see if they are still evident. Where these defects exist as part of a scripted scenario they will be run in parallel to test execution, otherwise they will be run once test execution is complete.
Functionality |  | Total Defects | Total Defects retested | Total Defects Yet to retested | Total Defects still evident | Total Defects no longer evident | Percentage of Total Defects Still Evident | Percentage of Defects No Longer evident | Defects NA
FS1 |  | 28 | 39 | 2 | 34 | 5 | 87.18% | 12.82% | 4
FS2 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 43
FS3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FS4 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Test Execution Status From ALM - Columbus NI 7.10 - PMS SIT | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
NI Baseline - Overall count | 1281 | 418 | 1266 | 0 | 1184 | 82 | 2 | 10 | 3 | 98.83% | 93.52%
Basic Dispensing | 340 | 169 | 340 | 0 | 306 | 34 | 0 | 0 | 0 | 100% | 90%
Label Printing | 76 | 0 | 76 | 0 | 66 | 10 | 0 | 0 | 0 | 100% | 86.84%
Patient Management | 19 | 0 | 19 | 0 | 15 | 4 | 0 | 0 | 0 | 100% | 78.95%
Prescriber and Practice Management | 25 | 7 | 25 | 0 | 20 | 5 | 0 | 0 | 0 | 100% | 80%
Endorsement | 84 | 0 | 84 | 0 | 75 | 9 | 0 | 0 | 0 | 100% | 89.29%
2DRx | 260 | 33 | 256 | 0 | 246 | 10 | 1 | 0 | 3 | 98.46% | 96.09%
MUR | 25 | 0 | 15 | 0 | 10 | 5 | 0 | 10 | 0 | 60% | 66.67%
Nexphase Migration | 243 | 0 | 242 | 0 | 237 | 5 | 1 | 0 | 0 | 99.59% | 97.93%
Automation Regression | 209 | 209 | 209 | 0 | 209 | 0 | 0 | 0 | 0 | 100% | 100%
Defect Validation Testing- Columbus Wales 7.10 - PMS SIT
Functionality |  | Total Defects | Total Defects retested | Total Defects Yet to retested | Total Defects still evident | Total Defects no longer evident | Percentage of Total Defects Still Evident | Percentage of Defects No Longer evident | Defects NA | Defects Blocked | As part of the process of running the baseline tests all existing defects will be retested to see if they are still evident. Where these defects exist as part of a scripted scenario they will be run in parallel to test execution, otherwise they will be run once test execution is complete.
NI Baseline |  | 40 | 39 | 0 | 20 | 19 | 51.28% | 48.72% | 0 | 1
Test Execution Status From ALM - Columbus NI 7.10 - PMS UAT | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
NI Baseline - Overall count | 309 | 123 | 285 | 0 | 257 | 28 | 24 | 0 | 0 | 92.23% | 90.18%
Patient Management | 9 | 2 | 9 | 0 | 7 | 2 |  |  |  | 100% | 77.78%
Endorsement | 41 | 17 | 41 | 0 | 39 | 2 |  |  |  | 100% | 95.12%
2DRx | 37 | 5 | 36 | 0 | 34 | 2 | 1 |  |  | 97.3% | 94.44%
MUR | 7 | 2 | 7 | 0 | 4 | 3 |  |  |  | 100% | 57.14%
Automation - Installments | 6 | 6 | 6 | 0 | 6 |  |  |  |  | 100% | 100%
Automation -Private prescription report | 16 | 16 | 16 | 0 | 16 |  |  |  |  | 100% | 100%
Automation - Basic dispensing | 14 | 13 | 14 | 0 | 7 | 7 |  |  |  | 100% | 50%
Defects associated to UJ's | 1 | 0 | 0 | 0 |  |  | 1 |  |  | 0% | 0%
Scan Article - ON
DDS | 2 | 0 | 2 | 0 | 1 | 1 |  |  |  | 100% | 50%
Emergency Supply | 6 | 0 | 6 | 0 | 6 |  |  |  |  | 100% | 100%
Instalments | 11 | 6 | 11 | 0 | 10 | 1 |  |  |  | 100% | 90.91%
Simple Instalments | 7 | 0 | 7 | 0 | 6 | 1 |  |  |  |  | 85.71%
Offline | 12 | 0 | 0 | 0 |  |  | 12 |  |  | 0% | 0%
Owings | 10 | 0 | 10 | 0 | 8 | 2 |  |  |  | 100% | 80%
Private Prescription Book | 21 | 16 | 21 | 0 | 19 | 2 |  |  |  | 100% | 90.48%
Private Prescriptions | 6 | 0 | 6 | 0 | 6 |  |  |  |  | 100% | 100%
Quad Stamp | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 100% | 100%
Reports | 10 | 0 | 10 | 0 | 8 | 2 |  |  |  | 100% | 80%
Scan Article | 8 | 0 | 8 | 0 | 8 |  |  |  |  | 100% | 100%
Shortcut Keys | 5 | 0 | 5 | 0 | 4 | 1 |  |  |  | 100% | 80%
Training Mode | 2 | 0 | 0 | 0 |  |  | 2 |  |  | 0% | 0%
Uncatalogued Products | 3 | 0 | 3 | 0 | 3 |  |  |  |  | 100% | 100%
Vet Dispensing | 3 | 0 | 3 | 0 | 3 |  |  |  |  | 100% | 100%
Visually Impaired | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 100% | 100%
Automation - Endorsement | 17 | 17 | 17 | 0 | 17 |  |  |  |  | 100% | 100%
Automation - 2DRx | 5 | 5 | 5 | 0 | 5 |  |  |  |  | 100% | 100%
Automation - MUR | 2 | 2 | 2 | 0 | 2 |  |  |  |  | 100% | 100%
Automation - Regression | 16 | 16 | 16 | 0 | 16 |  |  |  |  | 100% | 100%
Scan Article - OFF
DDS | 2 | 0 | 1 | 0 |  | 1 | 1 |  |  | 50% | 0%
Emergency Supply | 4 | 0 | 4 | 0 | 4 |  |  |  |  | 100% | 100%
Instalments | 3 | 0 | 3 | 0 | 3 |  |  |  |  | 100% | 100%
Offline | 6 | 0 | 0 | 0 |  |  | 6 |  |  | 0% | 0%
Owings | 5 | 0 | 5 | 0 | 5 |  |  |  |  | 100% | 100%
Private Prescriptions | 4 | 0 | 4 | 0 | 3 | 1 |  |  |  | 100% | 75%
Training Mode | 1 | 0 | 0 | 0 |  |  | 1 |  |  | 0% | 0%
Uncatalogued Products | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 100% | 100%
Vet Dispensing | 1 | 0 | 1 | 0 | 1 |  |  |  |  | 100% | 100%
Visually Impaired | 2 | 0 | 2 | 0 | 2 |  |  |  |  | 100% | 100%
Defect Validation Testing- Columbus NI 7.10 - PMS UAT | [9 empty] | As part of the process of running the baseline tests all existing defects will be retested to see if they are still evident. Where these defects exist as part of a scripted scenario they will be run in parallel to test execution, otherwise they will be run once test execution is complete.
Functionality |  | Total Defects | Total Defects retested | Total Defects Yet to retested | Total Defects still evident | Total Defects no longer evident | Percentage of Total Defects Still Evident | Percentage of Defects No Longer evident | Defects NA
NI Baseline |  | 21 | 16 | 0 | 14 | 2 | 87.5% | 12.5% | 5
Test Execution Status From ALM - Columbus Wales 7.10 - Stock+ SIT & UAT (Joint) | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
FS5 Regression- Overall count | 51 | 0 | 47 | 0 | 41 | 6 | 0 | 4 | 0 | 92.16% | 87.23%
FS5 - Scan Article - ON | 51 | 0 | 47 | 0 | 41 | 6 | 0 | 4 | 0 | 92.16% | 87.23%
Stock+ | 60 | 0 | 5 | 55 | 5 | 0 | 0 | 0 | 0 | 8.333% | 100%
Patient Management | 19 |  | 18 | 1 | 15 | 3 | 0 | 0 | 0 | 94.74% | 83.33%
Prescriber and Practice Management | 25 | 7 | 23 | 2 | 20 | 3 | 0 | 0 | 0 | 92% | 86.96%
Endorsement | 84 |  | 70 | 14 | 68 | 2 | 0 | 0 | 0 | 83.33% | 97.14%
2DRx | 260 | 33 | 250 | 6 | 241 | 9 | 0 | 0 | 4 | 96.15% | 96.4%
MUR | 25 |  | 15 | 0 | 10 | 5 | 0 | 10 | 0 | 60% | 66.67%
Nexphase Migration | 243 | 0 | 66 | 168 | 64 | 2 | 0 | 9 | 0 | 27.16% | 96.97%
Stock+ | 51 | 0 | 47 | 0 | 41 | 6 | 0 | 4 | 0 | 92.16% | 87.23%

## FS5_NI_BL_Execution status (hidden)
NI PMS Baseline - Overall - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 1702
Test cases Executed | 1653 | 97.12%
In Progress | 3 | 0.1763%
Yet to Run | 0 | 0%
Blocked | 15 | 0.8813%
NA | 31
Passed | 1503 | 90.93%
Failed | 150 | 9.074%
Remaining Scripts for exe | 18 | 1.058%
Test Cases Planned for today | 0
Test Cases Executed today | 5
NI PMS - SIT - 7.10 - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 1321
Test cases Executed | 1305 | 98.79%
In Progress | 3 | 0.2271%
Yet to Run | 0 | 0%
Blocked | 11 | 0.8327%
NA | 2
Passed | 1203 | 92.18%
Failed | 102 | 7.816%
Remaining Scripts for exe | 14 | 1.06%
Test Cases Planned for today | 0
Test Cases Executed today | 5
NI PMS - UAT - 7.10- Execution Status
Test Execution Status | Count | %age
Total Test Cases | 330
Test cases Executed | 301 | 91.21%
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 29
Passed | 259 | 86.05%
Failed | 42 | 13.95%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
Wales Stock+- SIT&UAT - 7.10 - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 51
Test cases Executed | 47 | 92.16%
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 4 | 7.843%
NA | 0
Passed | 41 | 87.23%
Failed | 6 | 12.77%
Remaining Scripts for exe | 4 | 7.843%
Test Cases Planned for today | 0
Test Cases Executed today | 0

## Jenner_R2_Daywise Exec (hidden)
Jenner_R2_12.0- Overall - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2018-04-26 | 55 | 32 |  | 2018-04-26 | 55 | 32
| 2018-04-27 | 195 | 154 |  | 2018-04-27 | 250 | 186
| 2018-04-30 | 194 | 181 |  | 2018-04-30 | 444 | 367
| 2018-05-01 | 5 | 5 |  | 2018-05-01 | 449 | 372
| 2018-05-02 | 80 | 53 |  | 2018-05-02 | 529 | 425
| 2018-05-03 | 75 | 62 |  | 2018-05-03 | 604 | 487
| 2018-05-04 | 51 | 54 |  | 2018-05-04 | 655 | 541
| 2018-05-07 | 30 | 67 |  | 2018-05-07 | 685 | 608
| 2018-05-08 | 0 |  |  | 2018-05-08 | 685
PMS -Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-26 | 10 | 0 | Environment was available at 5.00 PM IST and only Sanity testing is performed | 2018-04-26 | 10 | 0
| 2018-04-27 | 80 | 85 |  | 2018-04-27 | 90 | 85
| 2018-04-30 | 77 | 79 |  | 2018-04-30 | 167 | 164
| 2018-05-01 | 0 | 0 |  | 2018-05-01 | 167 | 164
| 2018-05-02 | 0 | 0 |  | 2018-05-02 | 167 | 164
| 2018-05-03 | 0 | 0 |  | 2018-05-03 | 167 | 164
| 2018-05-04 | 0 | 0 |  | 2018-05-04 | 167 | 164
| 2018-05-07 | 0 | 0 |  | 2018-05-07 | 167 | 164
| 2018-05-08 | 0 |  |  | 2018-05-08 | 167
EPS - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 | 0 | 0 |  | 2018-04-23 | 0 | 0
| 2018-04-24 | 0 | 0 |  | 2018-04-24 | 0 | 0
| 2018-04-25 | 0 |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 | 0 |  |  | 2018-04-26 | 0 | 0
| 2018-04-27 | 0 |  |  | 2018-04-27 | 0 | 0
ETC - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-26 | 33 | 20 | Productivity impacted has delay in starting testing - 4.30 pm IST | 2018-04-26 | 33 | 20
| 2018-04-27 | 12 | 13 |  | 2018-04-27 | 45 | 33
| 2018-04-30 | 12 | 8 | Stockplus GoodsIn related test cases are blocked due to TECR 24290 - CEMS investigating the same. | 2018-04-30 | 57 | 41
| 2018-05-01 | 0 | 0 |  | 2018-05-01 | 57 | 41
| 2018-05-02 | 0 | 0 | Stockplus GoodsIn related test cases blocked due to CSR job unknown status - COBA-6881 and OSU not received from AHDL | 2018-05-02 | 57 | 41
| 2018-05-03 | 0 | 0 | Stockplus test cases are blocked due to OSUs not received in IT5 Environment. Testing will be resumed once the OSU issue resolved | 2018-05-03 | 57 | 41
| 2018-05-04 | 0 | 3 | OSUs is received in IT5 Environment around 2.30 pm IST. Due now tests are blocked due to CSR issue(COBA-6881). | 2018-05-04 | 57 | 44
| 2018-05-07 | 0 | 13 | Testing completed | 2018-05-07 | 57 | 57
| 2018-05-08 | 0 | 0 |  | 2018-05-08 | 0 | 57
Stock Plus - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-26 | 12 | 12 |  | 2018-04-26 | 12 | 12
| 2018-04-27 | 81 | 32 | 1.calculateStockRequirement Job Failed Status in IT5 Environment 2.OSUs not received in IT5 Environment | 2018-04-27 | 93 | 44
| 2018-04-30 | 81 | 72 | 1.calculateStockRequirement Job Unknown Status in IT5 Environment 2.OSUs not received in IT5 Environment 3.jobCloseGoodsReceipt Job in Failed status | 2018-04-30 | 174 | 116
| 2018-05-01 | 5 | 5 |  | 2018-05-01 | 179 | 121
| 2018-05-02 | 80 | 53 | 1.calculateStockRequirement Job Unknown Status in IT5 Environment 2.OSUs not received in IT5 Environment until now | 2018-05-02 | 259 | 174
| 2018-05-03 | 75 | 62 | OSUs not received in IT5 Environment until now | 2018-05-03 | 334 | 236
| 2018-05-04 | 51 | 51 | 1.calculateStockRequirement Job Unknown Status in IT5 Environment 2.OSUs not received in IT5 Environment until 2:30 PM IST. | 2018-05-04 | 385 | 287
| 2018-05-07 | 30 | 54 |  | 2018-05-07 | 415 | 341
| 2018-05-08 | 0 | 66 |  | 2018-05-08 | 415 | 407
Optimus - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-26 | 0 | 0 |  | 2018-04-26 | 0 | 0
| 2018-04-27 | 22 | 24 |  | 2018-04-27 | 22 | 24
| 2018-04-30 | 24 | 22 | Testing completed | 2018-04-30 | 46 | 46
| 2018-05-01 | 0 | 0 |  | 2018-05-01 | 46 | 46
| 2018-05-02 | 0 | 0 |  | 2018-05-02 | 46 | 46
| 2018-05-03 | 0 | 0 |  | 2018-05-03 | 46 | 46
| 2018-05-04 | 0 | 0 |  | 2018-05-04 | 46 | 46
| 2018-05-07 | 0 | 0 |  | 2018-05-07 | 46 | 46
| 2018-05-08 | 0 |  |  | 2018-05-08 | 46
ST Testing - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-26 | 0 | 0 |  | 2018-04-26 | 0 | 0
| 2018-04-27 | 0 | 0 |  | 2018-04-27 | 0 | 0
| 2018-04-30 | 0 | 0 |  | 2018-04-30 | 0 | 0
| 2018-05-01 | 0 | 0 |  | 2018-05-01 | 0 | 0
| 2018-05-02 | 0 | 0 |  | 2018-05-02 | 0 | 0
| 2018-05-03 | 0 | 0 |  | 2018-05-03 | 0 | 0
| 2018-05-04 | 0 | 0 |  | 2018-05-04 | 0 | 0
| 2018-05-07 | 0 | 0 |  | 2018-05-07 | 0 | 0
| 2018-05-08 | 0 |  |  | 2018-05-08 | 0
Formulas:
Date = [Date]

## Jenner_R2_Exec Status (hidden)
Release 12.0_R2- Overall Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 30
Test Cases Executed today | 67
PMS - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
EPS - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | #REF!
Test Cases Executed today | #REF!
ETC - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
Stock plus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 66
Optimus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
ST Testing - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | 0 | 0%
Yet to Run | 0 | 0%
Blocked | 0 | 0%
NA | 0
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | 0 | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0

## Jenner_R3_Daywise Exec (hidden)
Jenner_R3_12.0- Overall - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2018-04-23 | 0 | 0 |  | 2018-04-23 | 0 | 0
| 2018-04-24 | 0 | 0 |  | 2018-04-24 | 0 | 0
| 2018-04-25 | 0 | 0 |  | 2018-04-25 | 0 | 0
| 2018-04-26 | 0 |  |  | 2018-04-26 | 0
| 2018-04-27 | 0 |  |  | 2018-04-27 | 0
PMS -Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 |  |  |  | 2018-04-23 | 0 | 0
| 2018-04-24 |  |  |  | 2018-04-24 | 0 | 0
| 2018-04-25 |  |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 |  |  |  | 2018-04-26 | 0
| 2018-04-27 |  |  |  | 2018-04-27 | 0
EPS - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 | 0 | 0 |  | 2018-04-23 | 0 | 0
| 2018-04-24 | 0 | 0 |  | 2018-04-24 | 0 | 0
| 2018-04-25 | 0 |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 | 0 |  |  | 2018-04-26 | 0 | 0
| 2018-04-27 | 0 |  |  | 2018-04-27 | 0 | 0
ETC - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 | 0 |  |  | 2018-04-23 | 0 | 0
| 2018-04-24 | 0 |  |  | 2018-04-24 | 0 | 0
| 2018-04-25 | 0 |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 | 0 |  |  | 2018-04-26 | 0
| 2018-04-27 | 0 |  |  | 2018-04-27 | 0
Stock Plus - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 |  |  |  | 2018-04-23 | 0 | 0
| 2018-04-24 |  |  |  | 2018-04-24 | 0 | 0
| 2018-04-25 |  |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 |  |  |  | 2018-04-26 | 0
| 2018-04-27 |  |  |  | 2018-04-27 | 0
Optimus - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 |  |  |  | 2018-04-23 | 0 | 0
| 2018-04-24 |  |  |  | 2018-04-24 | 0 | 0
| 2018-04-25 |  |  |  | 2018-04-25 | 0 | 0
| 2018-04-26 |  |  |  | 2018-04-26 | 0 | 0
| 2018-04-27 |  |  |  | 2018-04-27 | 0 | 0
ST Testing - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test Cases | Reason for Deviation | Date | Planned Test cases | Actual Test Cases
| 2018-04-23 |  |  |  | 2018-04-23 | 0 | 0
| 2018-04-24 |  |  |  | 2018-04-24 | 0 | 0
| 2018-04-25 |  |  |  | 2018-04-25 | 0
| 2018-04-26 |  |  |  | 2018-04-26 | 0
| 2018-04-27 |  |  |  | 2018-04-27 | 0

## Jenner_R3_Prog by Func (hidden)
Test Execution Status From ALM - Columbus 12.0_R3 - Overall | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
PMS SIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
EPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
ETC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Optimus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Stock+ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
System Testing - TSF-N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Test Execution Status From ALM - PMS | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Defect Retesting | [9 empty] | 0% | 0%
Firefox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
PMS Regression | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
2DRx | [9 empty] | 0% | 0%
Basic dispensing | [9 empty] | 0% | 0%
DUR and RESIP | [9 empty] | 0% | 0%
Label Printing | [9 empty] | 0% | 0%
Owings Management | [9 empty] | 0% | 0%
Private Prescriptions | [9 empty] | 0% | 0%
Scan Article | [9 empty] | 0% | 0%
Specials/Extemps | [9 empty] | 0% | 0%
Vet Dispensing | [9 empty] | 0% | 0%
Endorsements | [9 empty] | 0% | 0%
End to End Test cases | [9 empty] | 0% | 0%
Nexphase Migration | [9 empty] | 0% | 0%
CHS - Non eMAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
End to End Test cases | [9 empty] | 0% | 0%
CHS - eMAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
End to End Test cases | [9 empty] | 0% | 0%
IMS Data Feed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
IMS Data Feed | [9 empty] | 0% | 0%
Offline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
PMS Offline | [9 empty] | 0% | 0%
Test Execution Status From ALM - EPS | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R1 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Defect Retesting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Firefox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Oracle Compatible Mode Disabled - Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
MD Publish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Test Execution Status From ALM - ETC | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Defect Retesting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Firefox | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
MD Publish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
Test Execution Status From ALM - Stock plus | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
CHS Functionality | [9 empty] | 0% | 0%
Close PO | [9 empty] | 0% | 0%
Due Date Order & Report | [9 empty] | 0% | 0%
Due Now Calculations | [9 empty] | 0% | 0%
Due Now order | [9 empty] | 0% | 0%
Exception Count | [9 empty] | 0% | 0%
Lapse | [9 empty] | 0% | 0%
Manual Order | [9 empty] | 0% | 0%
Overstocks and report | [9 empty] | 0% | 0%
Owing Order | [9 empty] | 0% | 0%
Perform Goods In | [9 empty] | 0% | 0%
Pick List | [9 empty] | 0% | 0%
Telesales Order | [9 empty] | 0% | 0%
E2E_SCAN_ON_WALES_NI | [9 empty] | 0% | 0%
Stock+_Min_Max | [9 empty] | 0% | 0%
Test Execution Status From ALM - Optimus | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
SIT Stages 3 & 4 | [9 empty] | 0% | 0%
End 2 End Testing | [9 empty] | 0% | 0%
Migration Testing | [9 empty] | 0% | 0%
Test Execution Status From ALM - ST Testing | [10 empty] | 2023-04-23
Functionality | Total Test cases | Automated | Executed Count | Yet To Run | Passed | Failed | N/A | Blocked | In Progress | Percentage of Total Tests Executed | Executed Pass Percentage
R3 Regression - Overall Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Train 2 - Scenarios | [9 empty] | 0% | 0%

## Jenner_R3_Exec Status (hidden)
Release 12.0_R3- Overall Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | #REF!
Test Cases Executed today | #REF!
PMS - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | #REF!
Test Cases Executed today | #REF!
EPS - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | #REF!
Test Cases Executed today | #REF!
ETC - Execution Status
Test Execution Status | Count | %age
Total Test Cases | 0
Test cases Executed | 0 | #DIV/0!
In Progress | #REF! | 0%
Yet to Run | 0 | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | 0 | 0%
Failed | 0 | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
Stock plus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 65
Test Cases Executed today | 65
Optimus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 18
Test Cases Executed today | 10
ST Testing - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0

## Day wise - Burn Down
Overall RTL - Day Wise Burn Down
Cumulative
| Date | Daily Planned | Daily Actual | Reason for Deviation | Date | Planned Burn Down | Actual Burn Down
Total Test case count
| 2023-04-22 | 6.8 | 6 |  | 2023-04-22 | 34 | 34
| 2023-04-23 | 6.8 | 6 |  | 2023-04-23 | 27.2 | 28
| 2023-04-24 | 6.8 | 3 |  | 2023-04-24 | 20.4 | 22
| 2023-04-25 | 6.8 | 2 |  | 2023-04-25 | 13.6 | 19
| 2023-04-26 | 6.8 | 4 |  | 2023-04-26 | 6.8 | 17
| 2023-04-27 | 0 |  |  | 2023-04-27 | 0 | 13
Formulas:
Date = [Date]

## Overall Execution Status
Overall RTL Test Execution Status | [10 empty] | 2023-04-23
Functionality | Total Test cases | Executed Count | Yet To Run | Unexecuted | Passed | Failed | Blocked | In Progress | NA | % of Tests Executed | Executed Pass %
Overall Count | 33 | 33 | 0 | 0 | 22 | 9 | 2 | 0 | 0 | 100% | 66.67%
Feature Login | 6 | 6 |  | 0 | 6 | 0 | 0 | 0 | 0 | 100% | 100%
Feature Add to Cart | 4 | 4 |  | 0 | 3 | 1 | 0 | 0 | 0 | 100% | 75%
Feature Burger menù | 4 | 4 |  | 0 | 3 | 1 | 0 | 0 | 0 | 100% | 75%
Feature Checkout | 8 | 8 |  | 0 | 5 | 1 | 2 | 0 | 0 | 100% | 62.5%
Feature Inventory | 5 | 5 |  | 0 | 0 | 5 | 0 | 0 | 0 | 100% | 0%
Feature Remove Products | 3 | 3 |  | 0 | 2 | 1 | 0 | 0 | 0 | 100% | 66.67%
Social | 3 | 3 |  | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100%

## Mini_Exec Status (hidden)
Release 20.0- Overall RTL Execution Status |  |  | Release 19.0- Overall Non-RTL Execution Status |  |  |  |  | Release 20.0- Overall Non RTL Execution Status
|  |  |  | Count | %age
Test Execution Status | Count | %age |  | 0 |  | Count | %age | Test Execution Status | Count | %age
Total Test Cases | 33 |  |  | #REF! | #REF! | #REF! |  | Total Test Cases | #REF!
Test cases Executed | 33 | 100% |  | 0 | 0% | #REF! | #REF! | Test cases Executed | #REF! | #REF!
In Progress | 0 | 0% |  | #REF! | 0% | #REF! | 0% | In Progress | #REF! | 0%
Yet to Run | 0 | 0% |  | 0 | 0% | #REF! | 0% | Yet to Run | #REF! | 0%
Blocked | 0 | 0% |  | 0 |  | #REF! | 0% | Blocked | #REF! | 0%
NA | 2 |  |  | #REF! | 0% | #REF! |  | NA | #REF!
Passed | 22 | 66.67% |  | 0 | 0% | #REF! | 0% | Passed | #REF! | 0%
Failed | 9 | 27.27% |  | #REF! | 0% | #REF! | 0% | Failed | #REF! | 0%
Remaining Scripts for exe | 0 | 0% |  | #REF! |  | #REF! | 0% | Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | #REF! |  |  | #REF! |  | #REF! |  | Test Cases Planned for today | 0
Test Cases Executed today | #REF! |  |  |  |  | #REF! |  | Test Cases Executed today | 0
PMS - Execution Status |  |  | AMS, UCF & MAS - Execution Status |  |  |  |  | Stock plus(CHS) - Execution Status
Test Execution Status | Count | %age | Test Execution Status |  |  | Count | %age | Test Execution Status | Count | %age
Total Test Cases | #REF! |  | Total Test Cases |  |  | #REF! |  | Total Test Cases | 60
Test cases Executed | #REF! | #REF! | Test cases Executed |  |  | #REF! | #REF! | Test cases Executed | 55 | 91.67%
In Progress | #REF! | 0% | In Progress |  |  | #REF! | 0% | In Progress | 0 | 0%
Yet to Run | 0 | 0% | Yet to Run |  |  | #REF! | 0% | Yet to Run | 0 | 0%
Blocked | #REF! | 0% | Blocked |  |  | #REF! | 0% | Blocked | 3 | 5%
NA | #REF! |  | NA |  |  | #REF! |  | NA | #REF!
Passed | #REF! | 0% | Passed |  |  | #REF! | 0% | Passed | 52 | 94.55%
Failed | #REF! | 0% | Failed |  |  | #REF! | 0% | Failed | 5 | 9.091%
Remaining Scripts for exe | #REF! | 0% | Remaining Scripts for exe |  |  | #REF! | 0% | Remaining Scripts for exe | 3 | 5%
Test Cases Planned for today | #REF! |  | Test Cases Planned for today |  |  | #REF! |  | Test Cases Planned for today | 0
Test Cases Executed today | #REF! |  | Test Cases Executed today |  |  | #REF! |  | Test Cases Executed today | 0
EPS - Execution Status |  |  | DSP Integration- Execution Status
Test Execution Status | Count | %age | Test Execution Status |  |  | Count | %age
Total Test Cases | #REF! |  | Total Test Cases |  |  | #REF!
Test cases Executed | #REF! | #REF! | Test cases Executed |  |  | #REF! | #REF!
In Progress | #REF! | 0% | In Progress |  |  | #REF! | 0%
Yet to Run | #REF! | 0% | Yet to Run |  |  | #REF! | 0%
Blocked | #REF! | 0% | Blocked |  |  | #REF! | 0%
NA | #REF! |  | NA |  |  | #REF!
Passed | #REF! | 0% | Passed |  |  | #REF! | 0%
Failed | #REF! | 0% | Failed |  |  | #REF! | 0%
Remaining Scripts for exe | #REF! | 0% | Remaining Scripts for exe |  |  | #REF! | 0%
Test Cases Planned for today | 0 |  | Test Cases Planned for today |  |  | 0
Test Cases Executed today | 0 |  | Test Cases Executed today |  |  | 0
ETC - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
Old & New Stock plus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
Optimus - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
ST Testing - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0
AMS, UCF & MAS - Execution Status
Test Execution Status | Count | %age
Total Test Cases | #REF!
Test cases Executed | #REF! | #REF!
In Progress | #REF! | 0%
Yet to Run | #REF! | 0%
Blocked | #REF! | 0%
NA | #REF!
Passed | #REF! | 0%
Failed | #REF! | 0%
Remaining Scripts for exe | #REF! | 0%
Test Cases Planned for today | 0
Test Cases Executed today | 0

## Instructions (hidden)
Introduction
This report is intended as a summary of the detailed reports from a number of test workstreams and is for executive consumption.
The report gathers information in a standard form from the contributing work streams. The data is COPY/ PASTE AS VALUES from the source spreadsheet. Care is needed when pasting information on to the report to be sure it is pasted in to the correct cells and the Report tab references cells on the other tabs to get the information.
Capturing data
The contributing detailed reports are in a common format. There is a DAILY SUMMARY tab in the contributing spreadsheet where the data for this report is assembled.
Select the daily summary tab and select the entire content of the tab by clicking on the arrow head in the top left corner of the sheet.
Copy the selection.
Switch to the Combined Daily Summary report spreadsheet and open the tab corresponding to the source report you just captured data from. Position the cursor in cell A1 and PASTE VALUES in to this cell.
Repeat this process for each report going in to the Summary Report.
Finishing the Report (One Off Checks)
When a new release starts some data such as the duration of the test activity may impact the location and extent of the source of data, particularly for charts. The following checks need to be undertaken to ensure that the report functions correctly.
Check that the references to data on the REPORT tab still reflect the data positions on the project tabs.
In this example the Start date for Stock plus is pulled from the Stock plus tab cell E4. Check all the data fields still map correctly.
The riskiest data is that which produces the graphs and the number of rows might increase or decrease between releases. Check and adjust the graphs as follows:
Select the chart to be validated on the report and select CHART TOOLS and then Select Data
The following panel will open and you need to check the three (3) data elements match the data to be displayed on the chart. Two (2) on the left half and one (1) on the right half. The method of changing is the same except the ones on the left need to be selected by clicking on the label and then press the Edit button.
Edit the data as follows:
Click in the data source element of the panel and this will highlight the data in range with a broken line. If the data needs adjusting click on the start of the data and drag the cursor down to the end of the data range and click ok. Repeat for each data source. Check each chart in the report is working correctly.
Finishing the Report (Daily Checks)
A feature of the copy and paste corrupts the graphs on the report. Correct this using the following steps:
Navigate to the tab(s) that hold the report data. Find the blank cells below the Actual Journeys (col F, r 23), select them and press delete.
Select the REPORT tab and review the information. Check the values look reasonable and that the graphs are displaying correctly, there are no funny dates (01/01/1900) or spurious zero values anywhere. Correct any broken data.
Add comentary in the comments space at the top of the rpoert and then publish it to the circulation list.
Report Publishing
Executive Summary report - copy the Report from the Report tab of this spreadsheet and PASTE SPECIAL PICTURE ENHANCED METAFILE into an email and distribute to the executive distribution list.
Stream DSR Reports:
Paste an image of the report into an email, attach the stream DSR spreadsheet to the email and distribute to the appropriate distribution list :

## Distribution Lists (hidden)
Wales Stock plus | Optimus | PMS
Abhijit Akhuj <Abhijit.Akhuj@boots.co.uk> | a.augusto@emminformatica.it | Adam J Brown <Adam.J.Brown@boots.co.uk>
Adam J Brown <Adam.J.Brown@boots.co.uk> | Abhijit Akhuj <Abhijit.Akhuj@boots.co.uk> | Aishwarya Kamaraj <Aishwarya.Kamaraj@boots.co.uk>
Amandine Wray <amandine.wray@boots.co.uk> | Adam J Brown <Adam.J.Brown@boots.co.uk> | Amandine Wray <amandine.wray@boots.co.uk>
Ancel Mitchell <Ancel.Mitchell@boots.co.uk> | Amandine Wray <amandine.wray@boots.co.uk> | Ancel Mitchell <Ancel.Mitchell@boots.co.uk>
'antonio.improta@alliance-healthcare.net' | Ancel Mitchell <Ancel.Mitchell@boots.co.uk> | Anithakumari S <Anithakumari.S@boots.co.uk>
AntonyJude K <AntonyJude.K@boots.co.uk> | 'antonio.improta@alliance-healthcare.net' | Anton Byfleet <Anton.Byfleet@boots.co.uk>
Arulmurugan Mani <arulmurugan.mani@boots.co.uk> | Arulmurugan Mani <arulmurugan.mani@boots.co.uk> | Arulmurugan Mani <arulmurugan.mani@boots.co.uk>
Cacciapuoti, Giuseppe <Giuseppe.Cacciapuoti@alliance-healthcare.net> | Chris Watts <chris.watts@boots.co.uk> | Aruna Jayabalan <Aruna.Jayabalan@boots.co.uk>
Chris Watts <chris.watts@boots.co.uk> | giorgio.galiero@alliance-healthcare.net | Bathur Jaman A <BathurJaman.A@boots.co.uk>
Dawn Williams <dawn.williams@boots.co.uk> | 'Kerry, Patrick (Cognizant)' <Patrick.Kerry@cognizant.com> | Dinesh Devarajan <Dinesh.Devarajan@boots.co.uk>
Deepan Balaji <Deepan.Balaji@boots.co.uk> | KishoreKumar.TP@cognizant.com | Elizabeth Coombes <Elizabeth.Coombes@boots.co.uk>
giorgio.galiero@alliance-healthcare.net | l.cerasuolo@emminformatica.it | Gunasundari M <Gunasundari.M@boots.co.uk>
Johanna Lewis <johanna.lewis@boots.co.uk> | 'm.ferrara@emminformatica.it' | Helen Sharp <Helen.Sharp@boots.co.uk>
Kerry Woodhouse <Kerry.Woodhouse@boots.co.uk> | Michele Pollard <michele.pollard@boots.co.uk> | 'Improta, Antonio (Antonio.Improta@alliance-healthcare.net)'
'Kerry, Patrick (Cognizant)' <Patrick.Kerry@cognizant.com> | 'Nicola.Raglia@alliance-healthcare.net' | Jodie Carter <Jodie.Carter@boots.co.uk>
KishoreKumar.TP@cognizant.com | Padmanaban, Kumaresan (Cognizant) <Kumaresan.Padmanaban@cognizant.com> | Jodie Carter <Jodie.Carter@boots.co.uk>
Louis Boamah <Louis.Boamah@boots.co.uk> | Paolo.Provitera@alliance-healthcare.net | Kailash.Moorthi <K.Pichandampalayam@boots.co.uk>
'm.ferrara@emminformatica.it' | r.giglio@emminformatica.it | Kerry, Patrick (Cognizant) <Patrick.Kerry@cognizant.com>
Michael Sheehan <michael.sheehan@boots.co.uk> | Satishkumar Srinivasan <S.Srinivasan@boots.co.uk> | Kishore Kumar <Kishore.Kumar@boots.co.uk>
Michele Pollard <michele.pollard@boots.co.uk> | Shankara Vellingiri <Shankara.Vellingiri@boots.co.uk> | Kumaragurubaran K <Kumaragurubaran.K@boots.co.uk>
'Nicola.Raglia@alliance-healthcare.net' | 'Vincenzo Martino' <v.martino@emminformatica.it> | Kumaresan Padmanaban <Kumaresan.Padmanaban@boots.co.uk>
Ninu Joy <Ninu.Joy@boots.co.uk> | w.mancuso@emminformatica.it | M Selvaraj <M.Selvaraj@boots.co.uk>
Padmanaban, Kumaresan (Cognizant) (Kumaresan.Padmanaban@cognizant.com) |  | Mark Jones <mark.jones@boots.co.uk>
Paolo.Provitera@alliance-healthcare.net |  | 'Maurizio Ferrara' <m.ferrara@emminformatica.it>
Pat Wood <pat.wood@boots.co.uk> |  | Michael Sheehan <michael.sheehan@boots.co.uk>
Priya Varadarajan <Priya.Varadarajan@boots.co.uk> |  | Narendra Thakkar <Narendra.Thakkar@boots.co.uk>
r.giglio@emminformatica.it |  | Nisha Unnikrishnan <Nisha.Unnikrishnan@boots.co.uk>
Richard Naylor <richard.naylor@boots.co.uk> |  | 'Paolo.Provitera@alliance-healthcare.net'
Roger Nichols <Roger.Nichols@boots.co.uk> |  | Priya Varadarajan <Priya.Varadarajan@boots.co.uk>
Satishkumar Srinivasan <S.Srinivasan@boots.co.uk> |  | Satishkumar Srinivasan <S.Srinivasan@boots.co.uk>
Senthil Nallaperumal <Senthil.Nallaperumal@boots.co.uk> |  | Selvasivasankar S <Selvasivasankar.S@boots.co.uk>
Shankara Vellingiri <Shankara.Vellingiri@boots.co.uk> |  | Shankara Vellingiri <Shankara.Vellingiri@boots.co.uk>
'Vincenzo Martino' <v.martino@emminformatica.it> |  | Sivakumar Munisamy <Sivakumar.Munisamy@boots.co.uk>
w.mancuso@emminformatica.it |  | Suganya Yuvaraj <Suganya.Yuvaraj@boots.co.uk>
Richard Oldfield <richard.oldfield@boots.co.uk> |  | 'Vincenzo Martino (v.martino@emminformatica.it)'
'Wanda Mancuso (w.mancuso@emminformatica.it)'
Michele Pollard <michele.pollard@boots.co.uk>
Execs |  | Consolidated list
Adrian Caines <Adrian.Caines@boots.co.uk> |  | a.augusto@emminformatica.it
Archana Huria <Archana.Huria@boots.co.uk> |  | Abhijit Akhuj <Abhijit.Akhuj@boots.co.uk>
'Di leva, Rosario' <rosario.Dileva@alliance-healthcare.net> |  | Adam J Brown <Adam.J.Brown@boots.co.uk>
'Di Marzio, Eugenio' <Eugenio.DiMarzio@alliance-healthcare.net> |  | Aishwarya Kamaraj <Aishwarya.Kamaraj@boots.co.uk>
Francesco FT. Testa <Francesco.Testa@alliance-healthcare.net> |  | Amandine Wray <amandine.wray@boots.co.uk>
Hossein.Parvin@allianceboots.com |  | Ancel Mitchell <Ancel.Mitchell@boots.co.uk>
Karl Harris <karl.harris@boots.co.uk> |  | Anithakumari S <Anithakumari.S@boots.co.uk>
'Kerry, Patrick (Cognizant)' <Patrick.Kerry@cognizant.com> |  | Anton Byfleet <Anton.Byfleet@boots.co.uk>
Leonardo Tantari <Leonardo.Tantari@boots.co.uk> |  | 'antonio.improta@alliance-healthcare.net'
'Mariano.Tricerri@alliance-healthcare.net' |  | AntonyJude K <AntonyJude.K@boots.co.uk>
Michael Vipond <michael.vipond@boots.co.uk> |  | Arulmurugan Mani <arulmurugan.mani@boots.co.uk>
Neil Younger <neil.younger@boots.co.uk> |  | Aruna Jayabalan <Aruna.Jayabalan@boots.co.uk>
Nigel Shortt <nigel.shortt@boots.co.uk> |  | Bathur Jaman A <BathurJaman.A@boots.co.uk>
Roger Nichols <Roger.Nichols@boots.co.uk> |  | Cacciapuoti, Giuseppe <Giuseppe.Cacciapuoti@alliance-healthcare.net>
Shakilabhanu Jabbar <Shakilabhanu.Jabbar@boots.co.uk> |  | Chris Watts <chris.watts@boots.co.uk>
Thomas McKay <thomas.mckay@boots.co.uk> |  | Dawn Williams <dawn.williams@boots.co.uk>
Richard Oldfield <richard.oldfield@boots.co.uk> |  | Deepan Balaji <Deepan.Balaji@boots.co.uk>
Dinesh Devarajan <Dinesh.Devarajan@boots.co.uk>
Elizabeth Coombes <Elizabeth.Coombes@boots.co.uk>
giorgio.galiero@alliance-healthcare.net
Gunasundari M <Gunasundari.M@boots.co.uk>
Helen Sharp <Helen.Sharp@boots.co.uk>
'Improta, Antonio (Antonio.Improta@alliance-healthcare.net)'
Jodie Carter <Jodie.Carter@boots.co.uk>
Johanna Lewis <johanna.lewis@boots.co.uk>
Kailash.Moorthi <K.Pichandampalayam@boots.co.uk>
Kerry Woodhouse <Kerry.Woodhouse@boots.co.uk>
Kerry, Patrick (Cognizant) <Patrick.Kerry@cognizant.com>
'Kerry, Patrick (Cognizant)' <Patrick.Kerry@cognizant.com>
Kishore Kumar <Kishore.Kumar@boots.co.uk>
KishoreKumar.TP@cognizant.com
Kumaragurubaran K <Kumaragurubaran.K@boots.co.uk>
Kumaresan Padmanaban <Kumaresan.Padmanaban@boots.co.uk>
l.cerasuolo@emminformatica.it
Louis Boamah <Louis.Boamah@boots.co.uk>
M Selvaraj <M.Selvaraj@boots.co.uk>
'm.ferrara@emminformatica.it'
Mark Jones <mark.jones@boots.co.uk>
'Maurizio Ferrara' <m.ferrara@emminformatica.it>
Michael Sheehan <michael.sheehan@boots.co.uk>
Michele Pollard <michele.pollard@boots.co.uk>
Narendra Thakkar <Narendra.Thakkar@boots.co.uk>
'Nicola.Raglia@alliance-healthcare.net'
Ninu Joy <Ninu.Joy@boots.co.uk>
Nisha Unnikrishnan <Nisha.Unnikrishnan@boots.co.uk>
Padmanaban, Kumaresan (Cognizant) (Kumaresan.Padmanaban@cognizant.com)
Padmanaban, Kumaresan (Cognizant) <Kumaresan.Padmanaban@cognizant.com>
Paolo.Provitera@alliance-healthcare.net
'Paolo.Provitera@alliance-healthcare.net'
Pat Wood <pat.wood@boots.co.uk>
Priya Varadarajan <Priya.Varadarajan@boots.co.uk>
r.giglio@emminformatica.it
Richard Naylor <richard.naylor@boots.co.uk>
Roger Nichols <Roger.Nichols@boots.co.uk>
Satishkumar Srinivasan <S.Srinivasan@boots.co.uk>
Selvasivasankar S <Selvasivasankar.S@boots.co.uk>
Senthil Nallaperumal <Senthil.Nallaperumal@boots.co.uk>
Shankara Vellingiri <Shankara.Vellingiri@boots.co.uk>
Sivakumar Munisamy <Sivakumar.Munisamy@boots.co.uk>
Suganya Yuvaraj <Suganya.Yuvaraj@boots.co.uk>
'Vincenzo Martino (v.martino@emminformatica.it)'
'Vincenzo Martino' <v.martino@emminformatica.it>
w.mancuso@emminformatica.it
'Wanda Mancuso (w.mancuso@emminformatica.it)'
Michele Pollard <michele.pollard@boots.co.uk>
Richard Oldfield <richard.oldfield@boots.co.uk>

## OAT (hidden)
COBA | SUMMARY | STATUS | COMMENTS
COBA-65498 | Add GCP "FMD Mobile Request Timeout" | Passed
COBA-64926 | Columbus loading with 3 minute delay when wildfly is stopped in offline enabled store | Blocked | Issue with Offline setup in Prod support environment.
COBA-64715 | [MERGE 20.0] - Unable to print the repeat request report in 'To Be Requested' tab of 'Repeat Queue' | Passed
COBA-64691 | Dispensing date is not printed on Bag Label - Star Printer | Passed
COBA-64110 | Help Button displays an Empty Page | Passed
COBA-64067 | Action Not allowed popup appears on Edit in Recent History page | Passed
COBA-63937 | Date of birth search does not work for all patients | Passed
COBA-63746 | MERGE Mini 20.0- Actioning Offline link displays Online Log in Page and vice versa | Passed
COBA-63597 | MERGE 20.0 - Electronic Claimed Prescription and Item report is not printed from England stores | Passed
COBA-63263 | FMD-013M MOBILE Timeout | NA | Removed from Mini RTL scope, as FMD Mobile is not going live as part of Mini Release this weekend (20-Jul)
COBA-60535 | Houskeeping Procedures for Non Functional Table on Centralfilling schema | Passed
COBA-60528 | Houskeeping Procedures for DSP Stock Tables | Passed
COBA-60527 | Houskeeping Procedures for Orders Table on Centralfilling schema | Passed
COBA-60526 | Houskeeping Procedures for Central Filling Tables on Centralfilling schema | Passed
COBA-2887 | Houskeeping Procedures for GoodsIn Table | Passed
COBA-2886 | Houskeeping Procedures for Stock Tables | Passed
COBA-52977 | Improve the DPQ solution to report the correct outcome to control-m | Passed

## Automation (hidden)
Click here for legacy Automation Execution Details
RTL Mini - Overall - Day Wise Execution Plan - Non legacy Automation
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2019-06-19 | 0 | 0 |  | 2019-06-19 | 0 | 0
| 2019-06-20 | 42 | 42 |  | 2019-06-20 | 42 | 42
| 2019-06-21 | 42 | 42 |  | 2019-06-21 | 84 | 84
| 2019-06-22 | 0 | 0 |  | 2019-06-22 | 84 | 84
| 2019-06-23 | 0 | 0 |  | 2019-06-23 | 84 | 84
| 2019-06-24 | 96 | 96 |  | 2019-06-24 | 180 | 180
| 2019-06-25 | 96 | 91 |  | 2019-06-25 | 276 | 271
| 2019-06-26 | 96 | 99 |  | 2019-06-26 | 372 | 370
| 2019-06-27 | 96 | 115 |  | 2019-06-27 | 468 | 485
| 2019-06-28 | 197 | 202 |  | 2019-06-28 | 665 | 687
| 2019-06-29 | 0 | 0 |  | 2019-06-29 | 665 | 687
| 2019-06-30 | 0 | 0 |  | 2019-06-30 | 665 | 687
| 2019-07-01 | 192 | 152 |  | 2019-07-01 | 857 | 839
| 2019-07-02 | 125 | 125 |  | 2019-07-02 | 982 | 964
| 2019-07-03 | 126 | 126 |  | 2019-07-03 | 1108 | 1090
| 2019-07-04 | 63 | 63 |  | 2019-07-04 | 1171 | 1153
| 2019-07-05 | 63 | 63 |  | 2019-07-05 | 1234 | 1216
| 2019-07-06 | 0 | 0 |  | 2019-07-06 | 1234 | 1216
| 2019-07-07 | 0 | 0 |  | 2019-07-07 | 1234 | 1216
| 2019-07-08 | 40 | 35 |  | 2019-07-08 | 1274 | 1251
| 2019-07-09 | 0 | 23 |  | 2019-07-09 | 1274 | 1274
| 2019-07-10 | 40 | 40 |  | 2019-07-10 | 1314 | 1314
| 2019-07-11 | 55 | 55 |  | 2019-07-11 | 1369 | 1369
| 2019-07-12 | 25 | 25 |  | 2019-07-12 | 1394 | 1394
PMS -Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2019-06-19 | 0 | 0 |  | 2019-06-19 | 0 | 0
| 2019-06-20 | 42 | 42 |  | 2019-06-20 | 42 | 42
| 2019-06-21 | 42 | 42 |  | 2019-06-21 | 84 | 84
| 2019-06-22 | 0 | 0 |  | 2019-06-22 | 84 | 84
| 2019-06-23 | 0 | 0 |  | 2019-06-23 | 84 | 84
| 2019-06-24 | 0 | 0 |  | 2019-06-24 | 84 | 84
| 2019-06-25 | 0 | 0 |  | 2019-06-25 | 84 | 84
| 2019-06-26 | 0 | 0 |  | 2019-06-26 | 84 | 84
| 2019-06-27 | 0 | 0 |  | 2019-06-27 | 84 | 84
| 2019-06-28 | 0 | 0 |  | 2019-06-28 | 84 | 84
| 2019-06-29 | 0 | 0 |  | 2019-06-29 | 84 | 84
| 2019-06-30 | 0 | 0 |  | 2019-06-30 | 84 | 84
| 2019-07-01 | 62 | 62 |  | 2019-07-01 | 146 | 146
| 2019-07-02 | 62 | 62 |  | 2019-07-02 | 208 | 208
| 2019-07-03 | 62 | 62 |  | 2019-07-03 | 270 | 270
| 2019-07-04 | 0 | 0 |  | 2019-07-04 | 270 | 270
| 2019-07-05 | 0 | 0 |  | 2019-07-05 | 270 | 270
| 2019-07-06 | 0 | 0 |  | 2019-07-06 | 270 | 270
| 2019-07-07 | 0 | 0 |  | 2019-07-07 | 270 | 270
| 2019-07-08 | 0 | 0 |  | 2019-07-08 | 270 | 270
| 2019-07-09 | 0 | 0 |  | 2019-07-09 | 270 | 270
| 2019-07-10 | 40 | 40 |  | 2019-07-10 | 310 | 310
| 2019-07-11 | 55 | 55 |  | 2019-07-11 | 365 | 365
| 2019-07-12 | 25 | 25 |  | 2019-07-12 | 390 | 390
EPS - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2019-06-19 | 0 | 0 |  | 2019-06-19 | 0 | 0
| 2019-06-20 | 0 | 0 |  | 2019-06-20 | 0 | 0
| 2019-06-21 | 0 | 0 |  | 2019-06-21 | 0 | 0
| 2019-06-22 | 0 | 0 |  | 2019-06-22 | 0 | 0
| 2019-06-23 | 0 | 0 |  | 2019-06-23 | 0 | 0
| 2019-06-24 | 0 | 0 |  | 2019-06-24 | 0 | 0
| 2019-06-25 | 0 | 0 |  | 2019-06-25 | 0 | 0
| 2019-06-26 | 33 | 36 |  | 2019-06-26 | 33 | 36
| 2019-06-27 | 33 | 52 |  | 2019-06-27 | 66 | 88
| 2019-06-28 | 100 | 105 |  | 2019-06-28 | 166 | 193
| 2019-06-29 | 0 | 0 |  | 2019-06-29 | 166 | 193
| 2019-06-30 | 0 | 0 |  | 2019-06-30 | 166 | 193
| 2019-07-01 | 34 | 7 | CRAFT execution completed | 2019-07-01 | 200 | 200
| 2019-07-02 |  |  |  | 2019-07-02 | 200
| 2019-07-03 |  |  |  | 2019-07-03 | 200
| 2019-07-04 |  |  |  | 2019-07-04 | 200
| 2019-07-05 |  |  |  | 2019-07-05 | 200
| 2019-07-06 |  |  |  | 2019-07-06 | 200
| 2019-07-07 |  |  |  | 2019-07-07 | 200
| 2019-07-08 |  |  |  | 2019-07-08 | 200
| 2019-07-09 |  |  |  | 2019-07-09 | 200
| 2019-07-10 |  |  |  | 2019-07-10 | 200
ETC - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2019-06-19 | 0 | 0 |  | 2019-06-19 | 0 | 0
| 2019-06-20 | 0 | 0 |  | 2019-06-20 | 0 | 0
| 2019-06-21 | 0 | 0 |  | 2019-06-21 | 0 | 0
| 2019-06-22 | 0 | 0 |  | 2019-06-22 | 0 | 0
| 2019-06-23 | 0 | 0 |  | 2019-06-23 | 0 | 0
| 2019-06-24 | 33 | 33 |  | 2019-06-24 | 33 | 33
| 2019-06-25 | 33 | 33 |  | 2019-06-25 | 66 | 66
| 2019-06-26 | 0 | 0 |  | 2019-06-26 | 66 | 66
| 2019-06-27 | 0 | 0 |  | 2019-06-27 | 66 | 66
| 2019-06-28 | 34 | 34 |  | 2019-06-28 | 100 | 100
| 2019-06-29 | 0 | 0 |  | 2019-06-29 | 100 | 100
| 2019-06-30 | 0 | 0 |  | 2019-06-30 | 100 | 100
| 2019-07-01 | 33 | 33 | CRAFT execution completed | 2019-07-01 | 133 | 133
| 2019-07-02 |  |  |  | 2019-07-02 | 133
| 2019-07-03 |  |  |  | 2019-07-03 | 133
| 2019-07-04 |  |  |  | 2019-07-04 | 133
| 2019-07-05 |  |  |  | 2019-07-05 | 133
| 2019-07-06 |  |  |  | 2019-07-06 | 133
| 2019-07-07 |  |  |  | 2019-07-07 | 133
| 2019-07-08 |  |  |  | 2019-07-08 | 133
| 2019-07-09 |  |  |  | 2019-07-09 | 133
| 2019-07-10 |  |  |  | 2019-07-10 | 133
Old & New Stock Plus - Day Wise Execution Plan
Cumulative
| Date | Planned Test cases | Actual Test cases | Reason for Deviation | Date | Planned Test cases | Actual Test cases
| 2019-06-19 | 0 | 0 |  | 2019-06-19 | 0 | 0
| 2019-06-20 | 0 | 0 |  | 2019-06-20 | 0 | 0
| 2019-06-21 | 0 | 0 |  | 2019-06-21 | 0 | 0
| 2019-06-22 | 0 | 0 |  | 2019-06-22 | 0 | 0
| 2019-06-23 | 0 | 0 |  | 2019-06-23 | 0 | 0
| 2019-06-24 | 63 | 63 |  | 2019-06-24 | 63 | 63
| 2019-06-25 | 63 | 58 | 1. IT5-X Test Environment Down from 7.26 AMBST to 9.37 AM BST (2 Hours Down) for Mini Final Release deployment. 2. Osus were not received for the Stock Plus purchase orders placed in the test environment from offshore morning hours until 12.55PM BST, hence non OSU test cases were picked for test execution. | 2019-06-25 | 126 | 121
| 2019-06-26 | 63 | 63 |  | 2019-06-26 | 189 | 184
| 2019-06-27 | 63 | 63 |  | 2019-06-27 | 252 | 247
| 2019-06-28 | 63 | 63 |  | 2019-06-28 | 315 | 310
| 2019-06-29 | 0 |  |  | 2019-06-29 | 315 | 310
| 2019-06-30 | 0 |  |  | 2019-06-30 | 315 | 310
| 2019-07-01 | 63 | 50 | FT1-X/IT5-X environment downtime for Mini 20.1 Patch deployment from 9.45 AM BST to 11.30 AM BST (1.45 hours downtime) | 2019-07-01 | 378 | 360
| 2019-07-02 | 63 | 63 |  | 2019-07-02 | 441 | 423
| 2019-07-03 | 64 | 64 | 1. COBA-67163 – OSUs were not received in the test environments from offshore morning hours till 11.27 AM BST(6 hours down), hence Non OSU cases were executed 2. COBA-67273 – Intermittent could not send message in FT1-X environment | 2019-07-03 | 505 | 487
| 2019-07-04 | 63 | 63 | OSU's were not received and Jobs were not running -FT1 environment from 9.00 AM to 9.15 AM IST (15 mins down). Issue resolved by restarting jobs. TECR number : 38004 | 2019-07-04 | 568 | 550
| 2019-07-05 | 63 | 63 | OSU are note received in the test environments today. Raised COBA-67163 for tracking the issue. There are no sufficient OSU independent test cases for todays test exection and we will not be able to meet today target count | 2019-07-05 | 631 | 613
| 2019-07-06 | 0 |  |  | 2019-07-06 | 631 | 613
| 2019-07-07 | 0 |  |  | 2019-07-07 | 631 | 613
| 2019-07-08 | 40 | 35 | Unable to achieve the target because of the below OSU issues and there are no sufficient OSU independent test cases for execution. 1. COBA-67163 – OSUs were not received in the test environments from Offshore morning hours till 9.04 AM BST (4.30 Hours) . Once the OSU issue is resolved, we were not able to view the orders in LEO application. Issue resolved by AHDL by pointing the Leonardo client to the latest version at 12.30PM BST (3.30 Hours). 2. OSUs stopped again in the test environments from 13.18PM BST till 14.52PM BST. (1.30 Hours )Reopened COBA-67163 for tracking this issue. OSUs were not received in the test environments for 9.30 Hours | 2019-07-08 | 671 | 648
| 2019-07-09 | 0 | 23 | CRAFT Execution Completed | 2019-07-09 | 671 | 671
| 2019-07-10 | 0 |  |  | 2019-07-10 | 671
RTL Mini - Overall Execution Plan - legacy Automation - Bamboo Execution
Cumulative
Date | Planned Scenarios | Executed Scenarios | Bamboo Link | Reason for Deviation | Date | Planned Scenarios | Executed Scenarios
2019-07-02 | 1697 | 1692 | https://bamboo.tools.boots.com/browse/RTA-DV9AC | Object level changes impacts the rest of the cases | 2019-07-02 | 1697 | 1692
PMS
Cumulative
Date | Planned Scenarios | Executed Scenarios | Bamboo Link | Reason for Deviation | Date | Planned Scenarios | Executed Scenarios
2019-07-02 | 996 | 996 | https://bamboo.tools.boots.com/browse/RTA-DV9AC | Object level changes impacts the rest of the cases | 2019-07-02 | 996 | 996
Electronics
Cumulative
Date | Planned Scenarios | Executed Scenarios | Bamboo Link | Reason for Deviation | Date | Planned Scenarios | Executed Scenarios
2019-07-02 | 393 | 295 | https://bamboo.tools.boots.com/browse/RTA-DV9AC | Object level changes impacts the rest of the cases | 2019-07-02 | 393 | 295
2019-07-03 | 0 | 93 | https://bamboo.tools.boots.com/browse/RTA-DV9AC | Completed except 5 blocked cases | 2019-07-02 | 393 | 388
Workstream 2 - API Battery
Cumulative
Date | Planned Scenarios | Executed Scenarios | Bamboo Link | Reason for Deviation | Date | Planned Scenarios | Executed Scenarios
2019-07-02 | 308 | 308 | https://bamboo.tools.boots.com/artifact/RTA-CT1/JOB1/build-315/API-reports/report-tag_legacyworkstream2.html | Completed | 2019-07-02 | 308 | 308

## OAT Execution (hidden)
COBA | SUMMARY | Status | COBA #

## Sheet1 (hidden)
Issue key | Summary | Status | CBV | Severity
COBA-106722 | When moving to offline page , getting unexpected error & Online and offline prescription Sync is not working in Reconciliation tab | Open |  | CBV not yet assigned
COBA-106751 | OOPE AE is not sent in Resip request when the user add Additional Endorsement for AMS Prescription | Open |  | CBV not yet assigned

## Defects
ADO ID | Title | Status | Owner
Bug 1 | Inventory Home page – View of Product Selected is not matched with Product in Inventory list | Active | ? | Count of Issue key | Column Labels
Bug 2 | Inventory Item View – Add to Cart button is not working properly | Active | ? | Row Labels | Open | Grand Total
Bug 3 | Inventory Home Page View – Remove button is not working properly | Active | ? | CBV not yet assigned | 1 | 1
Bug 4 | “About” link is not working properly | Active | ?
Bug 5 | Sorting feature in Inventory Home Page is not working | Active | ? | Grand Total | 1 | 1
Bug 6 | Checkout: Your Information – Writing Last Name field with problem | Active | ?